## Slide 1: EpiScientia Network Kick-Off Meeting 10 July 2026
Nuraan Fakier

## Slide 2: EDCTP Association Role
  Monitor that all actions are implemented properly (e.g., respect of timelines regarding the submission of deliverables, etc)
  Submit deliverables and reports to Global Health EDCTP3
  Act as intermediary between beneficiaries and granting authorities (in collaboration with the Scientific Project Leader)
  Distribute payments received from EDCTP 3 to beneficiaries.
Deliverables:
Project Management Plan
Report on in-person meeting.
Please share any information (especially calls for training and Fellows), logos, videos, photos, or other communication materials: communications@global-health-edctp3.europa.eu
Project Management and Monitoring (Work Package 1) (M1-60)

## Slide 3: Scientific Project Leader (University of Rwanda)
Key contact point for scientific action governance issues, steer and provide oversight in the development of the scientific actions
Support and collaborate with the Coordinator on monitoring project progress
Review the action’s deliverables and reports
Lead the work packages(s) related to the tasks of scientific project leadership.
Post-award

## Slide 4: Reporting and Payment requirements
Lump sum costing

## Slide 5: Reporting and Payments

## Slide 6: Continuous reporting
Continuous reporting includes:
Progress in achieving Deliverables and Milestones
Update the public summary
Response to critical risks, publications, communication activities, results, etc.
Programme-specific monitoring information (if required)
Where? The Continuous Reporting Module is accessible in the EC Funding & Tender’s Portal
Who? Deliverables/Milestones should be uploaded by each beneficiary
What? Report on Deliverables/Milestones in accordance with the schedule (Annex 1).
In case of delays, please inform EDCTP3: relevant deliverables and milestones, months delay and reason -> no amendment is necessary (if only affects a few deliverables for a short period of time)
Article 21.1

## Slide 7: Periodic report
Part A (structured information entered through the continuous reporting module)
Project summary
Deliverables, milestones, risks, etc.
Answers to the impact questionnaire
Part B (narrative part submitted in a PDF through the periodic reporting module)
Explanation of work carried out by the beneficiaries and overview of progress
Explanations on deviations from DoA/Annex 1
Activated at the end of reporting periods
Must be submitted within 60 days following the end of each reporting period
M1-18
1
M19-36
2
M37-54
3
M54-60
4

## Slide 8: Status of the Work Packages
Submission by a coordinator
The coordinator declares work packages as Completed or Not Completed. This should be justified by the technical periodic report.
An incomplete work package can be completed and paid in a subsequent reporting period.
At the final reporting period, it is possible to declare Partially Completed work packages, and to enter the percentage of completion.

## Slide 9: Assessment of the WPs by the GH EDCTP3 PO
Completed vs. Partially completed
The PO will assess the technical report and the status of work packages
For each work package declared, the PO will assess and choose between Completed or Not Completed
At the final report, the project officer can also choose ‘Partially Completed ’ and enter the percentage of completion. The decision on the partial amount is taken on a case-by-case basis
The PO will reject a WP when a significant or essential part of the work has not been completed, and if the deviation from the work plan is not justified or not acceptable.
If the PO intends to reject a work package, you will have the opportunity to react to the observations of the PO.
In this case, the PO will either send you a request for additional information or reject the technical report and ask you to justify the completion of the work package(s).

## Slide 10: Amendments
Examples of cases where an amendment is necessary:
  Adding or removing a beneficiary, affiliated entity or associated partner
  Change of beneficiary due to partial takeover
  Changes to the Description of the Action (tasks, deliverables etc.).
Group together multiple changes into one amendment
The request for amendment must include the reasons why and the appropriate supporting documents
EDCTP 3 may request additional information
An amendment enters into force on the day of the signature of the receiving party
An amendment takes effect on the date agreed by the parties or, in the absence of such an agreement, on the date on which the amendment enters into force.